## Slide 1: I-24 CM/GC Project
December 18, 2018
CONTRACTOR PREPROPOSAL

## Slide 2: Pre-Proposal Agenda
Contractor Sign-In
Introductions and Opening Comments by TDOT
Purpose and Need
General Information
Project Overview
Roadway Bridges
South Germantown Road
Ramp Widening
TDOT Project Website
Questions

## Slide 3: Purpose and Need
Improve bridge along I-24
Wider roadway for wider shoulder widths
Build substructure to accommodate future road widening
Widen I-24 eastbound exit ramp at South Germantown Road to accommodate two (2) lanes
Improve bridge over I-24
Replace Belvoir Avenue Bridge
Intersection improvements at both bridges
Maintain or improve horizontal and vertical clearances
Minimize construction time and impacts by using Accelerated Bridge Construction (ABC)

## Slide 4: General Information from the RFP
Full closure of I-24 will be limited to up to 3 weekends
Maintain a minimum of 2 – 11’ lanes on I-24 in each direction on weekdays
SEE THE RFP FOR ALL THE DETAILS ON TRAFFIC CONTROL

## Slide 5: General Information from the RFP
CM will be a key part of the Integrated Project Team (TDOT, Design Consultant and Contractor)
As part of the Project Team see Section 1.1 of the RFP for skills and knowledge the CM agrees to provide during the design phase
All work shall occur within existing ROW
Early procurement or construction work may be considered for long lead items or early tasks

## Slide 6: General Information from the RFP
DBE Goal is 10.5%
Prohibited Contact
Minimum Statement of Interest (SOI) /Proposal Requirement
Bonding Requirement
Written Questions Only
Official Answers by QR Form
Section 1.22
Section 1.24
Section 2.1
Section 1.26
Section 2.5

## Slide 7: Proposed Schedule
TAKEN FROM SECTION 2.3 OF RFP
PHASE | ACTION | DATE
Public Notice Phase | First Advertisement of RFP | 11/30/18
 | Mandatory Pre-Proposal Meeting | 12/18/18
 | Last Submission of Questions/ Requested Clarifications | 01/07/19
 | Final RFP Addendum Deadline | 01/18/19
Selection Phase | Submittal of Statement of Interest (SOI)/Proposal | 01/25/19 2:00 PM(CST)/ 3:00 PM (EST)
 | Selection Panel Meetings (Interviews) | TBD
 | Contractor Notification of Selection | 02/22/19
 | Contract Approval/Execution | 03/22/19
ANTICIPATED CONSTRUCTION COMPLETION |  | OCTOBER 2020

## Slide 8: The Design Team
Project Lead
Roadway, Structural, Public Involvement, CM/GC Process, ITS, Utility Coordination, Traffic Control Design
Subconsultant
Geotechnical Engineering & Investigation

## Slide 9: Transportation Investment Report
TIR status
Approved
On the website
High level planning document
What does the TIR provide for the CM?
Good background
Constraints, needs, and desires
Initial stakeholders
Ideas to consider or build upon

## Slide 10: Traffic and Regional Impacts
I-24 CM/GC Project
US 27 Reconstruction
I-75/I-24 Design Build
132,293
119,177
113,090
28,255
120,655
70,349
Broad St & Market St Interchange

## Slide 11: Project Overview
24
INTERSTATE
South Germantown Road Exit Ramp Widening
Intersection Improvements
South Germantown Road Improvements
Interstate 24 Bridge Widening
Intersection Improvements
Belvoir Avenue Bridge Replacement
24
INTERSTATE

## Slide 12: Environmental Boundary

## Slide 13: Potential Staging Area

## Slide 14: Utilities Survey
SEE SURVEY FOR:
What is on the Bridges
What is adjacent to the Bridges
Elevation to OH Power Lines (on profiles)
Relocations are anticipated and will need to be identified early and coordinated

## Slide 15: Utilities Owners
Telephone
AT&T Southeast
611 Chestnut Street
Chattanooga, TN 37450
Tim Manley (423)752-9181
Cable
Comcast
537 Market Street
Chattanooga, TN 37402
Tom Bailey (423) 855-3900
Gas
Chattanooga Gas Company
6125 Preservation Drive
Chattanooga, TN 37416
Jana Papa (423) 490-4315
Power
E.P.B.
10 West M.L. King Boulevard
Chattanooga, TN 37402
Melvin Baumgarner (423) 648-3524
Water
TN American Water
1500 Riverside Drive
Chattanooga, TN 37406
Grady Stout
(423) 771-4713
Sewer
Hamilton County WWTA
1250 Market Street
Suite 3050
Chattanooga, TN 37402
(423) 209-7842

## Slide 16: Alternate Routes

## Slide 17: Existing & Proposed I-24 Typical Section

## Slide 18: Bridge 1: I-24 Over South Germantown Road

## Slide 19: Existing I-24 Bridge
166' – 4 span | 94’ existing width | Min. vert. clearance 14.44'
Tangent | 8' interior shoulders | 55mph speed limit
Concrete beams | Six 12' wide lanes | Underground culvert
79˚ skew | 3' exterior shoulders | 

## Slide 20: I-24 Existing Bridge Conditions
Looking North at Bent No. 2
Looking at Bents No. 1 & No. 2
Looking at Bent & Beam Support
Looking at Underside of Deck
Widened Bent Caps
Looking at Abutment No. 1

## Slide 21: I-24 Roadway Impacts
Minor approach work to I-24 roadway bridge
On South Germantown Road, additional road work needed at South Terrace intersection to improve sight distance
Adjust signage for new widening
Update traffic signals at interchange entrance/exit
Maintain positive drainage on all lanes and shoulders
Replace removed median barriers
Full depth pavement on shoulders or lanes excavated during construction
Full depth pavement on exit ramp widening during construction

## Slide 22: Existing & Proposed Belvoir Typical Section

## Slide 23: Bridge 2: Belvoir Avenue Bridge over I-24

## Slide 24: Existing Belvoir Bridge
190.5' – 4 Span | 78' Existing Width | Min. Vert. Clearance 16.33'
Normal | 4, 10' wide Lanes | 30 mph Speed Limit
Concrete Beams | 10' outside Shoulders | Electronic Message Board on I-24
90˚ Skew | 5' Sidewalks | 

## Slide 25: Belvoir Existing Bridge Conditions
No. 1 Right Side
Bridge Rail
Abutment No. 2
Approach No. 2
Span No. 3/Bent No. 2
Bent No. 3

## Slide 26: Belvoir Roadway Impacts
Minor approach work to Belvoir Avenue roadway at bridge
Mill, overlay, and stripe the Belvoir Avenue work zone
Adjust signage as needed
Update traffic signals on either side of bridge
Full depth pavement on shoulders or lanes excavated during construction

## Slide 27: Next Steps…
Initial Idea Development/ Technical Study
Continue Refinement of Concepts
CM and designer on-board
Additional stakeholder input
Begin Construction
Develop Solution

## Slide 28: Agency Stakeholders

## Slide 29: TDOT Project Website
SOURCE OF ALL OFFICIAL DOCUMENTATION
Only “Official Answers” to questions will be in writing
Additional Items will be placed on the website
  Current Survey
  Inspection Reports
  Previous Roadway and Bridge Plans
  Present Layouts, Profiles, Typical Sections and Property Maps

## Slide 30
https://www.tn.gov/tdot/tdot-construction-division/transportation-construction-alternative-contracting/cm-gc-project---interstate-24.html

## Slide 31: Proposed Design Build Schedule
ACTION | DATE
Anticipated NTP | 01/18/19
Begin Construction | 10/16/19
ANTICIPATED CONSTRUCTION COMPLETION | JUNE 2021

## Slide 32: Closing Comments
Thank you for your attendance
Questions?
Contact: Lia Obaid, PE
615.532.7522
Lia.Obaid@tn.gov

## Slide 33
Thank You!